## Slide 1: MAINTENANCE PLANNING AND ORGANIZATION OF MAINTENANCE PLANNING
Maintenance Planning is the advance preparation of selected jobs so that they can be executed in an efficient and effective manner when the job is performed at some future date.
Maintenance Planning is a process of detailed analysis to first determine and then to describe the work to be performed, by task sequence and methodology.
Maintenance Planning provides for the identification of all required resources, including skills, crew size, labor-hours, spare parts and materials, special tools and equipment.
Maintenance Planning includes developing an estimate of total cost and encompasses essential preparatory, post maintenance and restart efforts of both operations and maintenance.
<number>
Notes: <number>

## Slide 2: Why is Maintenance Planning Needed?
If the maintenance planning is professionally handled, the effective utilization of maintenance personnel can be increased by as much as 65% and job execution time can be reduced by as much as 40 to 50%.
The principal objectives of maintenance planning and scheduling include:-
Minimizing the idle time of maintenance forces;
Maximizing the efficient use of work time, material, and equipment; and
Maintaining the operating equipment at a level that is responsive to the need of production in terms of delivery schedule and quality.
<number>

## Slide 3: PRINCIPLES OF PLANNING
Understand the department's mission in relation to the objectives of the company;
Always be aware of the magnitude and trend or tendency of backlog or bottleneck;
Quantify the magnitude of the resources effectively available to apply toward relief of the backlog;
Establish a plan for the allocation of available resources to a balanced workweek, considering both long-range importance and short-range necessity;
Categorize work consistent with planned resource allocation categories;
<number>

## Slide 4: CONT.
Assign a planning priority (within job priority and category) to each job;
Break each job into logically sequenced tasks/activities;
Prepare a "Planning Week" schedule by phases of work planning and by task to determine progress toward completion of each week's work planning;
Work to meet this schedule. Protect it.
Measure progress and contribution.
<number>
Notes: <number>

## Slide 5: SEQUENCE OF PLANNING
Scheduling (when to do the job): Scheduling is the process by which required resources are allocated to specific jobs at a time the internal customer can make the associated equipment or job site accessible.
It is the process by which jobs are matched with resources (crafts) and sequenced to be executed at certain points in time.
<number>
Notes: <number>

## Slide 6
The maintenance schedule can be prepared in three levels depending on the horizon of the schedule.
The levels are:
medium range or master schedule to cover a period of 3 months to 1 year;
weekly schedule, it is the maintenance work that covers a week; and
the daily schedule covering the work to be completed each day.
<number>

## Slide 7: MAINTENANCE JOB PRIORITY SYSTEM
The maintenance job priority system has a remarkable impact on maintenance scheduling.
Priorities are established to ensure that the most critical and needed work is scheduled first.
Priority systems typically include three to ten levels of priority.
Most organizations adopt four or three level priorities.
Table below provides classification of the priority level and candidate jobs to be in each class as identified by Duffuaa
<number>
Notes: <number>

## Slide 8
Table :- Priorities of maintenance work
<number>

## Slide 9: SCHEDULING TECHNIQUES
Techniques are developed to develop optimum or near optimal schedules with respect to different possible performance measures.
These are:
1. Gantt Charts and Scheduling Theory
2. Project Scheduling
3. Critical Path Method
4. Program Evaluation Review Techniques (PERT)
<number>

## Slide 10: 1. GANTT CHARTS AND SCHEDULING THEORY
developed by Henry L. Gantt during World War II.
The Gantt chart is a bar chart that specifies the start and finish time for each activity on a horizontal time scale.
It is very useful for showing planned work activities vs accomplishments on the same time scale.
It can also be used to show the interdependencies among jobs, and the critical jobs that need special attention and effective monitoring.
<number>
Notes: <number>

## Slide 11
The following Figure shows the simplest form of the Gantt chart in which activities are scheduled at specified dates within the month.
<number>

## Slide 12: CONT.
Gantt charts can also be used to show the schedule for multiple teams or equipment simultaneously. A case in which three heavy pieces of equipment are scheduled for different jobs throughout the day as shown below.
The chart indicates that jobs 25A and 15D are completed on schedule,
job 25C is behind schedule by about a full day while job 25B is ahead of schedule by about a day, and
job 41E is in progress exactly on schedule.
Jobs 33C and 44E scheduled but have not started yet.
<number>

## Slide 13: CONT.
<number>

## Slide 14
Network Analysis for Planning and Control of Maintenance Work:-
Network analysis needs a group of techniques for presenting information relating to time and resources so as to assist in the planning, scheduling, and controlling of projects.
The information represented by network, includes the sequences, interdependencies, interrelationships, and critical activities of the project.
This is very useful for projects which are complex in nature or where activities are subject to considerable degree of uncertainty in performance time.
PROJECT SCHEDULING
<number>

## Slide 15: Applications of network techniques are very wide, but are very common in some of the following fields:
(i) Construction of buildings, bridges, highways, railways, stadiums, irrigation projects, factories, power projects etc.
(ii) Assembly line scheduling,
(iii) Development and launching of new products,
(iv) Strategic and tactical military planning,
(v) Research and development,
(vi) Market penetration programmed,
(vii) Planning of political campaigns,
(viii) Maintenance and overhauling of complicated or large machineries,
(ix) organizing big conferences etc.
<number>

## Slide 16: Advantages of Network Technique:
1. Detailed planning provides better analysis and logical thinking.
2. Identifies the critical activities and focus them to provide greater managerial attention.
3. Network technique enables to forecast project duration more accurately.
4. It is a powerful tool for optimization of resources.
5. It provides a scientific basis for monitoring, review and control, to evaluate effect of slippages.
6. It helps in taking decision;
7. It helps in getting better co-ordination amongst related fields.
8. It is an effective management tool through a common and simple language, providing common understand.
<number>
Notes: <number>

## Slide 17
Limitations of Network Techniques:
Network techniques have following limitations:-
Network technique is simply a tool to help the management; hence its effectiveness depends on how well it is used by the management.
Its accuracy depends on the estimation of the data used in the network.
It is useful only if it is updated regularly and decisions for corrective actions are taken timely.
<number>

## Slide 18: CONT.
The two primary network programming techniques used in project scheduling are the critical path method (CPM) and program evaluation and review technique (PERT)
The main difference between the two is that CPM uses a single estimate of activity time duration while PERT uses three estimates of time for each activity.
Hence, CPM is considered to be a deterministic network method while PERT is a probabilistic method.
<number>
Notes: <number>

## Slide 19
Cont.
Both networks consist of nodes representing activities and arrows indicating precedence between the activities.
The objective in both CPM and PERT is to schedule the sequence of work activities in the project and determine the total time needed to complete the project.
The total time duration is the longest sequence of activities in the network (the longest path through the network diagram) and is called the critical path.
Before we proceed by explaining the two methods it is worth noting that PERT and CPM are not well suited for day-to-day independent small jobs scheduling in a maintenance department.
<number>

## Slide 20
However, they are very useful in planning and scheduling large jobs (20 man hours or more) that consist of many activities such as machine overhauls, plant shut downs maintenance activities.
Furthermore, a prerequisite for the application of both methods is the representation of the project as a network diagram, which shows the interdependencies and precedence relationships among the activities of the project.
Formulating the maintenance project as a network diagram helps in viewing the whole project as an integrated system.
Interaction and precedence relationships can be seen easily and be evaluated in terms of their impact on other jobs.
<number>

## Slide 21: CONT
The project network representation will be demonstrated by an example from maintenance.
Next Table shows the data for repairing a bearing in a train cargo carriage. The data shows the normal, crash duration, their corresponding costs, and precedence or priority relationships for each activity. The term crash time refers to the minimum time the job can be accomplished in (by committing more resources), beyond which no further reduction in the job duration can be achieved. At this duration any increase in the resources for this job will increase the cost without reducing the duration.
<number>

## Slide 22
<number>

## Slide 23: CONT.
Next Figure shows the network corresponding to the data in the table. It starts with node A with no predecessor activity and it is represented by a circle nearby a number indicating the time. A itself is a predecessor for three activities B, C, and D drawn as three circles connected to A by arrows to indicate the precedence relation with A. Other activities (nodes) are traced back similarly. The resulting network is terminated by node I that has no successor.
<number>

## Slide 24: CONT.
<number>

## Slide 25: CONT.
There are many paths through the network in Figure starting from the first node to the last node. The longest one is called the critical path and the summation of the activity times along that path is the total project duration.
Jobs in the critical path are called critical in the sense that any delay in these jobs would cause a delay in the whole project.
All other paths include slack times (sometimes called floats), i.e. The amount of extra time that activities in the path can be delayed without delaying the completion time of the whole project. Activities that are not in the critical path may have some slack times, i.e., delaying this activity for one reason or another will not delay the whole project. In this example there are three possible paths shown in the next Table.
Critical activities must be monitored carefully and adhere to their specified schedules; however, non-critical activities can be used for leveling the resources due to the available slacks.
<number>

## Slide 26
Clearly the project duration is 467 min and the critical path is the first path (AB-E-G-H-I). Paths 2 and 3 have slacks of 167 and 277 min respectively. In this example, it was easy to go through all possible paths to find the one with the longest time; however, it would be extremely difficult to do the same for larger projects having a large number of activities and more complicated relationships between them. A systematic approach for identifying the critical path is known as the critical path method (CPM).
<number>

## Slide 27
To identify the critical path using the CPM method we need to follow the following steps:
1. Develop the project network diagram as shown in the previous section;
2. Perform the CPM calculation to identify the critical jobs (there are jobs on the critical paths and non-critical jobs (which are jobs with float);
3. Perform project crashing to (determine minimum times for each job) reduce project duration and investigate the cost tradeoffs; and
4. Level the resources in order to have uniform manpower requirements to minimize hiring, firing, or over time requirements.
3) Critical Path Method
<number>

## Slide 28: CONT.
The critical path calculation includes two phases. The first phase is the forward pass (starting with the first node and proceeding to the last node). In this phase, the earliest start time, ES, and earliest finish time, EF, are determined for each activity. The earliest start time Esi for a given activity, i, is the earliest possible time in the schedule that activity i can be started.
Its value is determined by summing up the activity times of the activities lying on the longest path leading to it.
The earliest finish time Efi for a given activity i, is its earliest start time plus its activity time Tai.
The calculations for the bearing overhaul example are shown in next Table.
<number>

## Slide 29
<number>

## Slide 30: CONT.
The second phase is the backward pass (starting with the last node and proceeding back to the first node).
We start this phase by assuming that the total project time Tcp, is the earliest finish time, EF, of the last activity found in the forward pass.
In this phase, the latest finish time, LF, and latest start time, LS, are determined for each activity.
The latest finish time Lfi for a given activity, i, is the latest possible time that activity i must be completed in order to finish the whole project on schedule. Its value is determined by - subtracting from Tcp the activity time along the longest path leading backward from the last node.
<number>

## Slide 31
For the last activity of the schedule, LF is set to be the total time duration of the project, Tcp. The latest finish time, LFi, for a given activity, i, is its latest finish time minus its activity time Tai.
The calculations for the bearing overhaul example are shown in Table.
<number>

## Slide 32
The last step in the analysis of the network is to determine the slack time for each activity Si
It can be determined by the difference between the latest and the earliest start time of the activity. The calculations are shown in Table below.
<number>

## Slide 33: CONT.
Note that the activities along the critical path (A-B-E-G-H-I) have zero slack times.
Activities not lying on the critical path have positive slacks, meaning that they could be delayed by an amount of time equal to their slack without delaying the project completion time.
The construction of the time chart should be made taking into consideration the available resources, and must take full advantage of the CPM calculation. In some circumstances it might not be possible to schedule many activities simultaneously because of personnel and equipment limitations. The total float for non-critical activities can be used to level the resources and minimize the maximum resource requirement.
<number>

## Slide 34: 4) Program Evaluation Review Techniques (PERT)
<number>

## Slide 35
Where i is an activity in the critical path
<number>

## Slide 36
<number>

## Slide 37
<number>

## Slide 38
Cont.
The critical path calculations lead to the same critical path obtained in the previous CPM calculations. The total project time is expected to be 467 min.
The estimated variance is 213.37 min. The probability that the project will complete in 467 min can be calculated from the standard normal distribution to be 0.5, or the project has a 50% chance of completing in 467 min. The probability that the project may finish in 500 min can be calculated as:
meaning that, the chance of completing the project in 500 min is almost 99%.
<number>

## Slide 39: CHAPTER 10. MAINTENANCE ORGANIZATION
Organizing is the process of arranging people and physical resources to carry out plans and accomplish organizational objectives.
  Organization is the process of identifying, classifying, grouping and assigning various activities/responsibilities/ and delegating authority and establishing relationships for the purpose of enabling to work most effectively together in the accomplishments of objectives:
<number>

## Slide 40
  The Organizing Process
  Determine tasks necessary to achieve objectives
  Create jobs and define their duties and responsibilities
  Group jobs into departments
  Create authority/reporting relationship
  Delegate authority
<number>

## Slide 41
Basic Management Organization Concepts
Establish reasonably clear division of authority with minimal overlap.
Authority can be divided functionally, geographically, or on the basis of expediency; or it can rest on some combination of all three
2. Keep vertical lines of authority and responsibility as short as possible.
Stacking layers of intermediate supervision, or the over application of specialized functional staff aides, must be minimized.
<number>

## Slide 42
3. Maintain an optimum number of people reporting to one individual.
Good organizations limit the number of people reporting to a single supervisor to between three and six.
4. Fit the organization to the personalities involved.
<number>

## Slide 43
Factors Affecting Maintenance Organization
Type of operation.
Maintenance may be predominant in a single area—buildings, machine tools, process equipment, piping, or electrical elements and this will affect the character of the organization and the supervision required.
2. Continuity of operations.
Whether an operation is a 5-day, single-shift or, roughly, a 7-day, three shifts makes a considerable difference in how the maintenance engineering department is to be structured and in the number of personnel to be included.
<number>

## Slide 44
3. Geographical situation.
The maintenance that works in a compact plant will vary from that the one that is dispersed through several buildings and over a large area.
4. Size of plant.
As with the geographical considerations above, the actual plant size will command the number of maintenance employees needed and the amount of supervision for this number.
<number>

## Slide 45
5. Scope of the plant maintenance department.
Inclusion of responsibility for a number of secondary functions means additional manpower and supervision.
6. Work-force level of training and reliability.
This highly variable characteristic has a strong impact on maintenance organization because it commands how much work can be done and how well it can be performed.
<number>

## Slide 46
Lines of Reporting for Maintenance
Many feel that a maintenance department functions best when it reports directly to top management.
If maintenance supervision considers itself part of production and its performance is evaluated in this light, it should report to the authority responsible for plant operations.
Maintenance engineering should report to a level that is responsible for the plant groups which it serves—plant manager, production superintendent, or manager of manufacturing — depending on the organization
<number>

## Slide 47
Specialized Personnel in Maintenance Organization
Technically Trained Engineers
Combining engineering and supervisory skills assures:
Rapid maturity of newly graduated personnel
Increasingly speedy work performance through shorter lines of communication.
An early introduction into the art of handling personnel, making them more adaptable to all levels of plant supervision.
Less resistance to new ideas.
<number>

## Slide 48
Staff Specialists
The use and number of staff specialists—electrical engineers, industrial engineers, metallurgists — depends on availability, required need for specialization, and the economics of a consulting service’s cost compared to that of employing staff experts.
Clerical Personnel
Paperwork should be minimized consistent with good operations and adequate control; the clerical staff should be designed to relieve supervision of routine paperwork that it can handle. The number of clerks used varies from 1 per 100 employees to 1 per 20 to 25 employees.
<number>

## Slide 49
Manpower Requirements
The number of employees— labor and supervision — to assure adequate plant maintenance coverage depends upon many factors.
Each plant must be treated as a separate problem with a consideration of all its unique aspects.
Hourly Personnel:
    Ratio of Maintenance Manpower to Total Operation Personnel
    Skills That Should Be Included.
<number>

## Slide 50
Selection and Training
a. Selection – Craft Personnel
Bases for selection could be:
  education,
  general intelligence,
  mechanical aptitude, and
  past experience
b. Training—Craft Personnel
  Formal Instruction
  Informal Instruction
  On-the-Job Training
<number>

## Slide 51
c. Selection—Supervisory Personnel
Although there are advantages in selecting people entirely from among maintenance employees, others who display leadership potential should be considered.
d. Training—Supervisory Personnel
This training consists of initial orientation; a formalized, sustained program of leadership training; and on-the-job coaching and consultation.
<number>

## Slide 52
Orientation gives the candidate basic data about the management team she/he is joining and about company and department policy.
Included also are facts about the scope of her/his personal responsibilities and the limits of the authority delegated to her/him.
Training ensuring continued effectiveness and improved performance should include such subjects as human relations, conducting of interviews, teaching methods, safety, and many more.
Goals of this part of the program should head toward increasing the candidate’s effectiveness as supervisor, teaching a feeling of unity with fellow managers, and enhancing personal development.
<number>

## Slide 53
On-the-job coaching is especially important for the beginning supervisor.
There is no substitute for regular, informal, personal contact with a superior concerning current technical, personal problems.
This type of development is a force for high morale and job satisfaction.
It should include both praise and criticism, the former sincere, the latter constructive.
<number>

## Slide 54
Area and Centralized Maintenance Control
Geography: The distribution of men, tools, material, etc., to positions within the plant site, geographically central meaning all men, tools, and material located at one point.
Organization: The direct organization control of craftsmen, including their supervision, scheduling, and guidance, organizationally central meaning the control of all maintenance in the facility by one person below the level of site manager.
<number>

## Slide 55
Various Combination
Organizationally Central
Organizationally Area
Geographically Area
Geographically Central
<number>

## Slide 56: THANK YOU !!
<number>